|  | WYNN RESORTS Office of the COO ¦ Strategy & Operations INTERNAL USE ONLY |
| --- | --- |

INTERNAL AUDIT REPORT
Enterprise OKR Framework -- Q1 2025

| OKR Cycle | Q1 2025 (Jan-Mar) |
| --- | --- |
| Facilitator | VP Strategy |
| Review Date | March 31 2025 |

Q1 2025 Enterprise OKRs

| Objective | Key Result | Owner | Target | Current Status | Confidence % |
| --- | --- | --- | --- | --- | --- |
| O1: Deliver industry-leading guest experience | KR1.1: Achieve NPS of 74 or above across both properties | VP Hotel Ops | 74 | 72 (Feb) | 75% |
| O1: Deliver industry-leading guest experience | KR1.2: Reduce VIP check-in wait time to under 3 minutes | VP Hotel Ops | Less than 3 min | 3.8 min (Feb) | 55% |
| O1: Deliver industry-leading guest experience | KR1.3: Achieve amenity delivery accuracy of 97% | Dir. Concierge | 97% | 93.1% (Feb) | 45% |
| O2: Drive operational efficiency to EBITDA margin 32%+ | KR2.1: Reduce staff absenteeism to 3.5% or below | VP HR | Less than 3.5% | 4.1% (Feb) | 50% |
| O2: Drive operational efficiency to EBITDA margin 32%+ | KR2.2: Achieve F&B order-to-delivery under 18 min | VP F&B | Less than 18 min | 20.2 min (Feb) | 60% |
| O2: Drive operational efficiency to EBITDA margin 32%+ | KR2.3: Complete Q1 CAPEX projects on schedule | VP Facilities | 100% on schedule | 87% on schedule | 70% |
| O3: Launch Lakeside Kitchen on time in June 2025 | KR3.1: Complete construction and fit-out by May 1 2025 | VP Facilities | May 1 2025 | On track | 80% |
| O3: Launch Lakeside Kitchen on time in June 2025 | KR3.2: Hire and train full F&B team by May 15 2025 | VP HR / VP F&B | May 15 2025 | 42% hired | 65% |
| O3: Launch Lakeside Kitchen on time in June 2025 | KR3.3: Complete all regulatory and health approvals by May 31 2025 | VP Legal | May 31 2025 | In progress | 70% |
| O4: Build high-performing cross-functional teams | KR4.1: Complete Q1 cross-departmental OKR alignment sessions | VP Strategy | 100% departments | 80% complete | 90% |
| O4: Build high-performing cross-functional teams | KR4.2: Reduce inter-departmental SLA breaches by 20% | VP IT / VP Ops | 20% reduction | 12% reduction YTD | 65% |
| O4: Build high-performing cross-functional teams | KR4.3: Achieve eNPS of 25+ across all operational departments | VP HR | 25+ | 22 (Feb) | 60% |