|  | WYNN RESORTS Office of the COO ¦ Organizational Excellence INTERNAL USE ONLY |
| --- | --- |

INTERNAL AUDIT REPORT
Change Management Initiative Outcomes -- FY2022 to FY2024

| Period | FY2022-FY2024 |
| --- | --- |
| Prepared By | Director of Organizational Excellence |
| Date | January 2025 |

Change Initiative Outcomes Register

| Initiative | Year | Scope | Change Type | Adoption Rate (90-day) | Attrition Impact | Achieved Stated Goal | Key Lessons |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Workday HCM Implementation | 2022 | All properties | Technology + Process | 61% | Temporary +1.2pp attrition in Q3 2022 | Partial -- payroll accuracy improved; scheduling module underused | Training was insufficient; managers needed 2x more support than budgeted |
| Service Recovery Program Redesign | 2022 | Hotel Operations | Process | 84% | No measurable impact | Yes -- complaint resolution time reduced 28% | Frontline involvement in design was the key success factor |
| New Table Games Changeover SOP | 2022 | Casino Operations | Process | 91% | No measurable impact | Yes -- downtime reduced from 22 min to 14 min | Simple, well-documented SOPs adopted faster than technology changes |
| Salesforce CRM Rollout (Marketing) | 2023 | Marketing + Casino Host | Technology | 48% | No measurable impact | No -- Casino Host adoption too low to deliver expected revenue uplift | Lacked exec sponsor; Casino Hosts not engaged in requirements gathering |
| Restructure of F&B Division | 2023 | F&B Operations | Organizational | 73% | Temporary +2.4pp attrition in roles affected by role redesign | Yes -- labor cost reduced 8.1%; RevPAC improved | Change communications were strong; transition support was adequate |
| Sustainability Program Launch | 2023 | All departments | Culture + Process | 67% | No measurable impact | Partial -- energy KPIs met; water KPIs missed | Culture change requires longer runway; operational targets achieved more easily than mindset change |
| New Hire Onboarding Redesign | 2024 | All departments | Process + Culture | 89% | Early data suggests -0.8pp 90-day attrition | Yes -- 90-day engagement score improved 9pp | Best-practice: co-designed with frontline team members |
| Digital Tipping Program | 2024 | F&B + Hotel | Technology | 77% | No measurable impact | Partial -- guest adoption 62%, below 80% target | Guest communication about the program was launched too late; needed pre-arrival touchpoints |