|  | WYNN RESORTS Office of the CTO ¦ Technology Strategy STRICTLY CONFIDENTIAL |
| --- | --- |

INTERNAL AUDIT REPORT
Build vs. Buy Decision Outcomes -- Historical Review FY2020-2024

| Period | FY2020-FY2024 |
| --- | --- |
| Prepared By | VP Technology Strategy |
| Date | January 2025 |

Historical Build / Buy Decision Outcomes

| Year | Decision Name | Category | Approach Chosen | Budget ($M) | Actual Cost ($M) | Delivered On Time? | ROI vs Projection | Lessons Learned |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2020 | Casino Marketing Automation | CRM / Marketing | Buy (Salesforce Marketing Cloud) | 1.8 | 2.1 | No (3 months late) | Below -- 62% of projected | Underestimated data migration complexity; Salesforce Marketing Cloud requires dedicated admin |
| 2021 | Mobile App (guest-facing) | Guest Technology | Build (internal) | 3.2 | 5.8 | No (8 months late) | Below -- 31% of projected | App store deployment and iOS/Android compatibility underestimated; should have been partner/buy |
| 2021 | Procurement Platform | Operations Technology | Buy (Coupa) | 1.4 | 1.6 | Yes (1 week late) | At target | SaaS buy decisions with clear vendor track records perform well when implementation is managed tightly |
| 2022 | HR & Payroll System | HR Technology | Buy (Workday) | 3.8 | 4.1 | No (2 months late) | At target (medium-term) | Workday implementations require dedicated internal project resource; do not depend entirely on SI |
| 2022 | Custom Analytics Dashboard | Business Intelligence | Build (internal) | 0.6 | 0.9 | No (4 months late) | Below -- 44% of projected | Analytics dashboards are poor candidates for custom builds; Tableau plugin would have been faster and cheaper |
| 2023 | Casino Host CRM Customization | CRM / Casino | Build (Salesforce custom) | 1.1 | 2.2 | No (6 months late) | Below -- 28% of projected | Custom Salesforce development requires specialized expertise not available internally; should have used ISV partner |
| 2023 | Cybersecurity SIEM Platform | Security | Buy (Microsoft Sentinel) | 0.8 | 0.8 | Yes | At target | Well-scoped buy decisions for security tooling consistently perform on time and on budget |
| 2024 | Digital Tipping Integration | Guest Technology | Partner (Tip Network SaaS) | 0.3 | 0.3 | Yes | Above target | Partner SaaS for discrete guest-facing features is consistently the fastest and best-value approach |